Заявка на финансирование гуманитарного проекта

«Открытие дома-музея имени Нины Дмитриевны Ковалёвой, как объекта социокультурного туризма и одно из направлений устойчивого развития региона»

| 1. | Наименование проекта | Открытие дома-музея имени Нины Дмитриевны Ковалёвой, как объекта социокультурного туризма и одно из направлений устойчивого развития региона |
| --- | --- | --- |
| 2. | Наименование организации | Государственное учреждение культуры «Дрибинская библиотечная сеть» |
| 3. | Физический и юридический адрес организации, телефон, факс, е-mail | 213971, Могилёвская область, г.п. Дрибин, ул. Ленина, д. 39 тел. +375224871568 е-mail: dribin.bib@tut.by |
| 4. | Информация об организации | Государственное учреждение культуры «Дрибинская библиотечная сеть» отдела идеологической работы, культуры и по делам молодёжи Дрибинского районного исполнительного комитета |
| 5. | Руководитель организации | Веремьёва Светлана Игоревна, директор, +375295453698 |
| 6. | Менеджер проекта | Астапова Кристина Валерьевна, заведующий отдела библиотечного маркетинга и рекламы, +375297492962 |
| 7. | Прежняя помощь, полученная от других иностранных источников | Помощь не оказывалась |
| 8. | Требуемая сумма | 29 900 USD |
| 9. | Софинансирование | 100 USD |
| 10. | Срок проекта | 12 месяцев |
| 11. | Цель проекта | Популяризация творчества талантливых литераторов-земляков, знакомство с их жизнью и творческим наследием, развитие социокультурной инфраструктуры и привлечение инвестиций в район. |
| 12. | Задачи проекта | 1. Оформить комнаты в доме-музее 2. Разработать цикл экскурсий по дому-музею 3. Включить посещение дома-музея в туристический маршрут «Зеленый маршрут» 4. Провести рекламную кампанию |
| 13. | Детальное описание деятельности в рамках проекта в соответствии с поставленными задачами | Отремонтировать все помещения в доме и фасад дома. Оформить экспозиции в комнатах. Закупить или реставрировать предметы интерьера. Разработать и распечатать рекламную продукцию. |
| 14. | Обоснование проекта | Нематериальное культурное наследие является одним из устойчивых факторов развития любого региона. Богата земля Дрибинская на уникальные самобытные промыслы и ремёсла, народное творчество, талантливых людей. Одной из таких людей являлась поэтесса-землячка, член Союза писателей Беларуси, инвалид 1 группы - Нина Дмитриевна Ковалёва (1949-2020). Литературное творчество поэтессы является ярким проявлением нематериальной культуры человека. В Темнолесской библиотеке-филиале Дрибинского района, на родине знаменитой землячки, создана литературно-музейная комната “Паэтычная зорка маленькай радзімы”, посвященная жизни и литературному наследию Н.Д.Ковалёвой, которая пользуется большой популярностью у жителей Дрибинского и соседних районов. Работа Темнолесской библиотеки-филиала по подготовке и открытию литературно-краеведческой музейной комнаты оценена на ХХII Республиканском конкурсе «Бібліятэка - асяродак нацыянальнай культуры» в номинации «За новации в библиотечном деле». Так, среди всех библиотек Могилевской области, только здесь работает литературно-краеведческая музейная комната, экспозиция которой посвящена поэту-земляку. В этом заключается уникальность и новизна как самой библиотеки, так и её работы по сохранению культурного наследия региона. Идея местной инициативы заключается в том, чтобы продолжить работу литературно-музейной комнаты в новом формате (дом-музей) и позиционировать его как объект социокультурного туризма, вовлечение населения, а также учреждений и организаций региона в развитие агроэкотуризма Дрибинского района посредствам экскурсионной работы в доме-музее, направленной на увеличение посещений туристами (в том числе иностранными) Дрибинского района. |
| 15. | Деятельность после окончания проекта | Данная инициатива получит дальнейшее развитие посредствам усовершенствования и расширения экспозиционной базы дома-музея. Распространение опыта будет проходить путём организации и проведения мастер-классов, обучающих семинаров, освещения опыта работы в республиканских и областных СМИ, в сети Интернет, организации работы в рамках туристических маршрутов |
| 16. | Бюджет проекта | 30 000 USD |

APPLICATION FOR FINANCING A HUMANITARIAN PROJECT

«Opening of the House-Museum named after Nina Dmitrievna Kovaleva as an object of socio-cultural tourism and one of the directions of sustainable development of the region»

| 1. | Project name | Opening of the House-Museum named after Nina Dmitrievna Kovaleva as an object of socio-cultural tourism and one of the directions of sustainable development of the region |
| --- | --- | --- |
| 2. | Name the organization | State Cultural Institution "Dribin Library Network" |
| 3. | The physical and legal address of the organization, phone, fax, е-mail. | Lenin Street, 39 Dribin, Mogilev Region phone. +375224871568. е-mail: dribin.bib@tut.by |
| 4. | Organization information | State Cultural Institution "Dribin Library Network" of the Department of Ideological Work, Culture and Youth Affairs of the Dribin District Executive Committee |
| 5. | Supervisor of the organization | Svetlana Igorevna Veremyeva- Director, phone. +375295453698 |
| 6. | Project manager | Kristina Valeryevna Astapova– The Head of the Library Marketing and Advertising Department, phone. +375297492962. |
| 7. | Previous assistance received from other foreign sources | No help was provided |
| 8. | Amount Required | 29 900 USD |
| 9. | Co-financing | 100 USD |
| 10. | Project term | 12 months |
| 11. | The purpose of the project | Popularization of creativity of talented writers-countrymen, acquaintance with their life and creative heritage, development of socio-cultural infrastructure and attraction of investments to the district. |
| 12. | Objectives of the project | 1. Design rooms in the House-Museum 2. Develop a cycle of excursions around the House-Museum 3. Include a visit to the House-Museum in the tourist route " Green route» 4. Conduct an advertising campaign |
| 13. | Detailed description of the project activities in accordance with the tasks | To repair all rooms in the house and the facade of the house. To make the exposition in the rooms. To buy or to restore the interior. To develop and to print advertising products. |
| 14. | Project justification | Intangible cultural heritage is one of the sustainable factors for the development of any region. The land of Dribin is rich in unique original crafts, folk art, talented people. One of these people was a poet-countrywoman, a member of the Union of writers of Belarus, a disabled person of group 1 - Nina Dmitrievna Kovaleva (1949-2020). Literary creativity of the poetess is a vivid manifestation of the intangible culture of man. In Temny Les, the homeland of the famous countrywoman, in one of the library branches in Dribin district Literary Museum Room “Poetic Star of a Small Homeland” was created, dedicated to the life and literary heritage of N. D.Kovaleva, which is very popular among residents of Dribin and neighboring areas. The Work of Temnolesskaya library branch on the preparation and opening of the Literary and Local History Museum Room was valued at the XXII national contest "Library is the center of national culture" in the nomination "For innovations in librarianship". So, among all the libraries of the Mogilev region, only here there is the Literary and Local History Museum Room, the exposition of which is dedicated to the poet-countrywoman. This is the uniqueness and novelty of both the library itself and its work to preserve the cultural heritage of the region. The idea of local initiatives is to continue the work of the Literary Museum Room in the new format (the House-Museum) and to position it as an object of socio-cultural tourism, the community and the institutions and organizations involvement in the development of rural tourism of Dribin district through tours to the House-Museum. It is aimed at increasing visits by tourists (including foreign) of Dribin district. |
| 15. | Activities after the end of the project | This initiative will be further developed through the improvement and expansion of the exposition base of the House-Museum. The dissemination of experience will take place through the organization and conduct of master classes, training seminars, coverage of work experience in the Republican and Regional media, on the Internet, organization of work within the framework of tourist routes |
| 16. | Project budget | 30 000 USD |